## Log
QC DISCREPANCY & PREVENTED-COST LOG
Claim collected Monday → condition verified during the week → the discrepancy is the output. DEMONSTRATION DATA — every job, person, and figure is fictional.
Entry # | Date Claimed | Job | Source | Claim (verbatim) | Date Verified | Found | Discrepancy | Driver | Prevented Cost $ | Basis for $ | Payer Avoided | Routed To | Status | Notes
1 | 2026-03-02 | Hotel L1 | Foreman | Short 6 closers on L3, need a reorder | 2026-03-04 | 5 closers staged in unit 312 under another heading's tags. 1 true gap: that heading was never released by the supplier. | Y | False shortage | 1850 | Reorder avoided: 5 closers @ $370 quoted | Company | Supplier | Routed | True gap routed as a supplier release, not a reorder.
2 | 2026-03-02 | Clinic TI | GC super | Doors on 2 are done | 2026-03-05 | 14 of 16 openings closed out. 2 missing closeout photo and fire-label check. | Y | Completion claim | 0 | No cost — held open until the closeout gate reads 100% | — | Foreman | Closed | Completion is a claim; verified is a gate.
3 | 2026-03-09 | Hotel L1 | Installer | Should be enough casing for L4 | 2026-03-11 | Casing on hand covers 31 of 38 openings; 7 pieces are the wrong profile for the openings they were staged at. | Y | Short | 266 | Wrong-profile order avoided: 7 pcs @ $38 | Company | PM | Closed | "Should be" is a non-answer. Counted per opening.
4 | 2026-03-09 | School Reno | Supplier | All hardware for wing A shipped on the BOL | 2026-03-10 | Count matched the slip. 1 carton damaged — photographed before signing. | N |  | 0 |  |  |  | Closed | Claim held. Damage claim filed separately.
5 | 2026-03-16 | Office Core | Foreman | Missing 12 hinges, crew is stopped | 2026-03-16 | Hinges in the staging cage, mis-sorted into another floor's boxes. | Y | False shortage | 540 | Expedite + reorder avoided: 12 @ $45 | Company | Foreman | Closed | Same-day walk. Crew restarted in an hour.
6 | 2026-03-16 | Hotel L1 | GC super | Frames on L5 are ready for doors | 2026-03-18 | 9 of 22 frames out of plumb beyond tolerance. Photographed and blocked before any door was hung. | Y | Sequencing | 2700 | Rehang labor avoided: 9 openings @ $300 est. | Company | GC | Routed | Frame correction is GC scope.
7 | 2026-03-23 | Clinic TI | Installer | Pulls are on site | 2026-03-24 | On site, staged by opening. | N |  | 0 |  |  |  | Closed
8 | 2026-03-23 | School Reno | Foreman | Short 9 bypass tracks | 2026-03-26 | 60-inch kits cut down for 48-inch openings. 9 unopened 48-inch kits still boxed on site. | Y | Waste | 1080 | Reorder avoided: 9 kits @ $120 | Company | Foreman | Closed | Field size-matching gap, not a short-ship. Remediation logged separately.
9 | 2026-03-30 | Office Core | Supplier | Set 7 hardware ships Friday | 2026-04-03 | Did not ship. ETA pushed 10 days. | Y | Short | 0 | Schedule risk only | Supplier | PM | Routed | Sequence resequenced around it.
10 | 2026-03-30 | Hotel L1 | Foreman | L3 doors all latching | 2026-04-01 | 3 of 18 would not latch from 90°. Gasketing installed over silencers. | Y | Completion claim | 0 | Caught before the GC walk | — | Foreman | Closed | Latching from any position is life-safety, not punch.
11 | 2026-04-06 | Clinic TI | GC super | Need 4 more kickplates — yours came short | 2026-04-07 | Kickplates not on the submittal for those openings. Take-off gap, not a short-ship. | Y | Scope | 360 | Absorbed cost avoided: 4 @ $90 | Company | GC | Routed | GC to direct as a change.
12 | 2026-04-06 | School Reno | Installer | Received everything for wing B | 2026-04-08 | Count matched. | N |  | 0 |  |  |  | Closed
13 | 2026-04-13 | Office Core | Foreman | Lever trim missing on 8 locks | 2026-04-14 | Staged, mislocated to floor 3. | Y | False shortage | 1120 | Reorder avoided: 8 @ $140 | Company | Foreman | Closed
14 | 2026-04-13 | Hotel L1 | PM | Door count on L6 matches the schedule | 2026-04-15 | Matches. | N |  | 0 |  |  |  | Closed
15 | 2026-04-20 | Clinic TI | Supplier | Electric strikes are fail-secure per spec | 2026-04-21 | 2 of 6 shipped fail-safe. | Y | Other | 500 | Rework avoided: 2 openings @ $250 labor | Supplier | Supplier | Closed | Wrong function shipped. Quarantined, swapped.
16 | 2026-04-27 | School Reno | Foreman | Short 3 doors in wing C | 2026-04-28 | Openings framed wider than the take-off; the doors on site are take-off size. | Y | Scope | 0 | Attribution pending | GC | GC | Open | Held for cost attribution before any order.

## Summary
RUNNING LEDGER
Computed from the Log tab. Nothing on this tab is typed.
HEADLINE
Total prevented cost | 8416 |  | Margin the checks protected.
Claims checked | 16 |  | Every claim verified — broken or not.
Discrepancies found | 12
Discrepancy rate | 75% |  | How often a stated position fails a walk.
Open / unrouted | 1 |  | A finding held quietly costs nobody anything. Route it.
BY JOB | Prevented $ | Discrepancies
Hotel L1 | 4816 | 4
Clinic TI | 860 | 3
School Reno | 1080 | 2
Office Core | 1660 | 3
Other | 0 | 0
BY DRIVER | Prevented $ | Count
False shortage | 3510 | 3
Rip | 0 | 0
Short | 266 | 2
Scope | 360 | 2
Waste | 1080 | 1
Sequencing | 2700 | 1
Completion claim | 0 | 2
Other | 500 | 1
The driver decides the payer — rip, short, scope, and waste each land on a different party. Without a baseline to attribute against, the cost defaults to whoever installs.

## Legend
HOW TO USE
Where to type | Log tab only, rows 5 onward. Entry # fills itself. Summary and Legend are automatic. Rows 5–20 are fictional examples — overwrite them.
Date Claimed | When the claim arrives — Monday, in the weekly status pull. The claim's date, not the walk's.
Job | Dropdown. Edit the list in Data Validation to match your jobs.
Source | Who stated the position. Dropdown.
Claim (verbatim) | Their words, not a paraphrase. "Should be," "mostly," "I believe so" are the tells — log them as said.
Date Verified | When the claim was walked.
Found | The physical condition. Factual, no interpretation.
Discrepancy | Y / N. Log the N's too — a discrepancy rate needs a denominator, and the claims that held are the evidence the check is fair.
Driver | What is actually behind it. Each driver has a different payer — that is the point of the column.
Prevented Cost $ | Dollars the company would have absorbed had the claim gone unchecked. Leave blank or zero when no cost was at stake.
Basis for $ | How the number was reached: quoted material cost, reorder value, labor estimate. A number with no basis does not survive a room.
Payer Avoided | Who would have paid. With no baseline, it defaults to the company.
Routed To | Where the finding landed: owner on money, supplier on supply, GC on site conditions, foreman on field process.
Status | Open / Routed / Closed. Open means it has not cost anyone anything yet.
THREE USES
Weekly | The discrepancy output goes out at the end of each week. That is the week's product.
Monthly | Totals by driver show where the process fails — which is where the next gate goes.
Any review | Show the ledger instead of arguing the point. The denominator is what makes it credible.